## Sheet1
description | Level 1 (catégorie) | Level 2 (sous-catégorie)
Vendor delivery schedule is not aligned with baseline | Project Controls | Project baseline
HAZOP validation needs final review | Engineering | Safety in design
QA/QC documentation has not been updated | Engineering | Other
Pipeline insulation review is delayed | Engineering | Technical peer reviews
Design interface alignment has inconsistencies | Engineering | Technical peer reviews
Contractor manpower planning requires verification | Construction | Management of contractors
Project kickoff readiness is missing key approvals | Engineering | Technical peer reviews
Review of procurement logs is incomplete | Engineering | Technical peer reviews
System performance test needs clarification from supplier | Engineering | Other
Risk register update lacks technical justification | Risk Assessment | Type 1 risk assessment
| Engineering | Technical peer reviews
| Engineering | Technical peer reviews
| Engineering | Technical peer reviews
Project Manager has not taken yet a specific training on Risk Management as per JESA Standard. | Risk Assessment | Type 1 risk assessment
Missing safety documentation during site inspection | hse | HSE inspections and assessments
assessment activities not conducted | Project Management | Scope definition
RCF has not been completed by the project team | Risk Assessment | Risk classification (RCF)